## Summary
eLEARNING MOBILE APP — FEATURE OVERVIEW
LearnDash / Kajabi / Teachable mobile app — full feature breakdown by tier
Tier | Focus | Build Phase | Feature Count | Done | Partial | Not available | Done %
Tier 1 — Core Learning | Video, progress, quizzes, catalogue | Phase 1 — MVP | 20 | 7 | 9 | 4 | 35%
Tier 2 — Engagement | Notifications, gamification, notes | Phase 1 — MVP | 22 | 0 | 0 | 22 | 0%
Tier 3 — Community | Forums, live sessions, cohorts | Phase 3 | 22 | 0 | 0 | 22 | 0%
Tier 4 — Monetisation | IAP, subscriptions, promo codes | Phase 3 | 22 | 1 | 1 | 19 | 4.545%
Tier 5 — AI Layer | AI tutor, adaptive paths, summaries | Phase 2 | 25 | 0 | 0 | 25 | 0%
Tier 6 — Platform and Ops | Dashboard, analytics, white-label | Phase 4 | 25 | 1 | 5 | 19 | 4%
TOTAL |  |  | 136 | 9 | 15 | 111 | 6.618%
Counts come from the 'App Status' column on each tier tab and update when a status is changed. Tier 4 row 9 is a note, not a feature, so it is marked N/A and not counted as Done. Status checked against the app and LearnDash Mobile API plugin 1.0.19 (main branch, 15 Oct 2026).

## Tier 1 - Core Learning
TIER 1 - CORE LEARNING
Must-have on day one
Feature Group | Feature / Description | Priority | Features currently available: - Playback speed controls (0.5x to 2x) - Quality selector (auto / 360p / 720p / 1080p) - Subtitles / closed captions | App Status | In Our App Today / What's Missing | Recommendation
Video Player | Offline download for on-the-go learning | P1 — Must Have |  | Done | Whole course downloads for offline use: MP4 videos, lesson text, images and materials, with pause/resume/cancel, progress and notifications. YouTube/Vimeo lessons still need internet. | Available now
| Playback speed controls (0.5x to 2x) |  |  | Done | 0.5x to 2x speed for self-hosted MP4 (player menu) and YouTube (speed chip). | Available now
| Resume from last position |  |  | Not available | Videos start from 0:00 every time; the playback position is not saved. | Next version
| Picture-in-picture mode |  |  | Not available | No picture-in-picture; video stops when the app is minimised. | Later version
| Subtitles / closed captions |  |  | Partial | YouTube videos show YouTube's own captions where available. No subtitle support for self-hosted MP4 videos. | Next version
| Quality selector (auto / 360p / 720p / 1080p) |  |  | Partial | YouTube adjusts quality automatically; no manual selector. MP4 plays the uploaded file as-is. | Later version
Progress Tracking | Per-lesson completion status | P1 — Must Have | All listed features are implemented | Done | Tick per lesson/topic in the curriculum, including progress made offline. | Available now
| Per-course progress bar |  |  | Done | Progress bar and 'X of Y completed' on the course page. | Available now
| Resume where you left off |  |  | Done | 'Continue' opens the next unfinished lesson; works offline for downloaded courses. | Available now
| Completion percentage on home screen |  |  | Partial | Shown on the course page and Profile stats; the home-screen course cards do not show a percentage. | Next version
Quizzes & Certificates | Multiple choice, true/false, short answer | P2 — Should Have | All listed features are implemented // Drip‑locked lesson feature is present, // but not yet tested to confirm if it unlocks upon quiz completion. | Done | Native in-app quiz: single and multiple choice (incl. true/false), free-text answer, sorting, fill-in-the-blank, matrix and assessment questions. | Available now
| Drip-locked lessons (unlock on passing quiz) |  |  | Partial | Drip by date and linear progression (next lesson locked until the previous one is done) work, also offline. Unlocking specifically on passing a quiz is not yet tested. | Next version
| Auto-generated completion certificates |  |  | Done | LearnDash certificate is available in the app once the course is completed. | Available now
| Shareable certificate (LinkedIn, PDF download) |  |  | Partial | Certificate downloads as a PDF and opens in the phone's viewer (can be shared from there). No LinkedIn or in-app share button. | Next version
| Quiz retake limits and cooldown timers |  |  | Partial | Retake limits are enforced by LearnDash when the quiz is submitted; the app does not show attempts left or a cooldown timer. | Later version
Course Catalogue | Search by keyword, topic, instructor | P2 — Should Have | Currently available on home screen: - Filter by Category | Partial | Search by keyword and by topic. No search by instructor. | Next version
| Filter by category, level, price, duration |  |  | Partial | Filter by category only. No level, price or duration filters. | Next version
| Course preview (free trailer) |  |  | Not available | No course trailer/preview in the app. | Later version
| Enrolment and one-click access |  |  | Partial | Enrolled courses open in one tap (Start / Continue). Enrolling itself happens on the website. | Next version
| Wishlist / save for later |  |  | Not available | No wishlist / save for later. | Later version

## Tier 2 - Engagement
TIER 2 - ENGAGEMENT
Drives retention and completion rates
Feature Group | Feature / Description | Priority | App Status | In Our App Today / What's Missing | Recommendation
Push Notifications | Daily learning reminders (user-set time) | P1 — Must Have | Not available | No push notifications. The app only notifies when a course download finishes. | Next version
| Streak alerts (Don't break your streak!) |  | Not available | No streaks or streak alerts. | Later version
| New lesson / content drop alerts |  | Not available | No push alert. In-app only: a downloaded course shows 'Updated on the site — download again' when content changes. | Next version
| Live session reminders |  | Not available | No live sessions. | Later version
| Assignment due date reminders |  | Not available | No assignments or due-date reminders. | Later version
Gamification | XP points per lesson completed | P1 — Must Have | Not available | No XP points. | Later version
| Badges and achievement unlocks |  | Not available | No badges or achievements. | Later version
| Course leaderboard (opt-in) |  | Not available | No leaderboard. | Later version
| Level system (Beginner to Expert) |  | Not available | No level system. | Later version
| Monthly challenge events |  | Not available | No challenge events. | Later version
Learning Streaks | Daily goal setting (15 min / 30 min / 1 hr) | P2 — Should Have | Not available | No daily goal setting. | Later version
| Calendar heatmap of activity |  | Not available | No activity heatmap. | Later version
| Streak freeze (grace day) |  | Not available | No streak freeze. | Later version
| Weekly summary card |  | Not available | No weekly summary. | Later version
Notes & Bookmarks | Timestamped notes inside video (tap to note at 4:32) | P2 — Should Have | Not available | No notes inside videos. | Later version
| Highlight key moments in transcripts |  | Not available | No transcripts or highlights. | Later version
| Personal notebook per course |  | Not available | No personal notebook. | Later version
| Export notes as PDF |  | Not available | No notes export. | Later version
Assignments & Projects | File upload submissions | P3 — Nice to Have | Not available | No assignment uploads in the app (LearnDash assignments must be submitted on the website). | Later version
| Instructor feedback with annotations |  | Not available | No instructor feedback view. | Later version
| Peer review workflows |  | Not available | No peer review. | Later version
| Submission deadline tracking |  | Not available | No deadline tracking. | Later version

## Tier 3 - Community
TIER 3 - COMMUNITY
Turns solo learning into belonging
Feature Group | Feature / Description | Priority | App Status | In Our App Today / What's Missing | Recommendation
Discussion Forums | Per-lesson comment threads | P1 — Must Have | Not available | No lesson comments. | Later version
| Per-course community feed |  | Not available | No community feed. | Later version
| Upvote / mark as helpful |  | Not available | No upvotes. | Later version
| Instructor pinned answers |  | Not available | No pinned answers. | Later version
| Rich text + image attachments |  | Not available | No rich-text posts. | Later version
Live Sessions | In-app Zoom / Google Meet integration | P1 — Must Have | Not available | No Zoom / Google Meet integration. | Later version
| Live session schedule on home screen |  | Not available | No live session schedule. | Later version
| Replay recordings linked to course |  | Not available | No recordings section. | Later version
| Q&A queue during live sessions |  | Not available | No live Q&A. | Later version
| Attendance tracking |  | Not available | No attendance tracking. | Later version
Cohort Groups | Batch-based groups (Jan cohort, March cohort) | P2 — Should Have | Not available | No cohort groups (LearnDash groups are not shown in the app). | Later version
| Group chat per cohort |  | Not available | No group chat. | Later version
| Shared progress view within cohort |  | Not available | No shared cohort progress. | Later version
| Accountability partner matching |  | Not available | No partner matching. | Later version
Instructor Direct Message | Async Q&A with instructor | P2 — Should Have | Not available | No instructor messaging. | Later version
| Voice message support |  | Not available | No voice messages. | Later version
| Response time indicator |  | Not available | No response-time indicator. | Later version
| Office hours booking (Calendly integration) |  | Not available | No office-hours booking. | Later version
Peer Networking | Learner profiles (skills, goals, location) | P3 — Nice to Have | Not available | Profile shows the learner's own name and course stats only. | Later version
| Connect / follow other learners |  | Not available | No follow/connect. | Later version
| Course alumni directory |  | Not available | No alumni directory. | Later version
| Study group creation |  | Not available | No study groups. | Later version

## Tier 4 - Monetisation
TIER 4 - MONETISATION
Revenue layer — critical for sustainability
Feature Group | Feature / Description | Priority | App Status | In Our App Today / What's Missing | Recommendation
In-App Purchases | Individual course purchases | P1 — Must Have | Not available | No in-app purchase; courses are bought on the website (see the note in row 9). | Later version
| Bundle / programme purchases |  | Not available | No bundle purchases in the app. | Later version
| Upsell prompts at course completion |  | Not available | No upsell prompts. | Later version
| One-click buy with saved payment method |  | Not available | No in-app payments. | Later version
| Note: Buy via web to avoid Apple 30% cut — app is consumption-only |  | N/A | Followed: the app is consumption-only and has no purchase flow. | Available now
Subscriptions | Monthly and annual plan options | P1 — Must Have | Not available | No subscriptions in the app (handled on the website). | Later version
| All-access vs category-specific tiers |  | Not available | No subscription tiers in the app. | Later version
| Free trial with card capture |  | Not available | No trial capture in the app. (The plugin's 15-day trial is a site licence, not a learner trial.) | Later version
| Pause subscription option |  | Not available | No pause option. | Later version
| Family / team plan |  | Not available | No family/team plans. | Later version
Promo Codes & Affiliates | Discount code entry at checkout | P2 — Should Have | Not available | No checkout in the app. | Later version
| Affiliate link tracking |  | Not available | No affiliate tracking. | Later version
| Referral rewards for learners |  | Not available | No referral rewards. | Later version
| Flash sale banners |  | Not available | No sale banners. | Later version
Wallet & Credits | In-app credit balance | P2 — Should Have | Not available | No credit balance. | Later version
| Gift cards (send to a friend) |  | Not available | No gift cards. | Later version
| Bulk seat purchasing for teams |  | Not available | No bulk seats in the app. | Later version
| Corporate invoice / PO support |  | Not available | No invoice / PO support in the app. | Later version
Free vs Paid Gating | Free preview lessons per course | P3 — Nice to Have | Not available | LearnDash sample (free preview) lessons are not shown as previews to non-enrolled learners. | Next version
| Locked lesson indicators |  | Done | Lock icons with reasons: 'Complete the previous lesson', drip date ('Available on …'), access expired or removed. | Available now
| Upgrade prompt at paywall moment |  | Partial | Non-enrolled learners see 'Access Restricted'; there is no upgrade or buy link to the website. | Next version
| Lead magnet free course to paid upsell |  | Not available | Free courses are marked FREE, but there is no free-to-paid upsell flow. | Later version

## Tier 5 - AI Layer
TIER 5 - AI LAYER
Your differentiator — where TeachOS plays
Feature Group | Feature / Description | Priority | App Status | In Our App Today / What's Missing | Recommendation
AI Tutor / Course Q&A | Course-scoped chatbot (only knows your content) | P1 — Must Have | Not available | Not built yet — no AI features in the app. | Later version
| Ask questions about a lesson mid-video |  | Not available | Not built yet — no AI features in the app. | Later version
| Socratic mode (guides, doesn't just answer) |  | Not available | Not built yet — no AI features in the app. | Later version
| Cites the exact lesson or timestamp for the answer |  | Not available | Not built yet — no AI features in the app. | Later version
| BYOK model support for enterprise clients |  | Not available | Not built yet — no AI features in the app. | Later version
Adaptive Learning Paths | Pre-assessment to place learner in right module | P1 — Must Have | Not available | Not built yet — no AI features in the app. | Later version
| Skip lessons the learner already knows |  | Not available | Not built yet — no AI features in the app. | Later version
| Resurface lessons where quiz scores were low |  | Not available | Not built yet — no AI features in the app. | Later version
| Dynamic reordering based on learning pace |  | Not available | Not built yet — no AI features in the app. | Later version
Smart Lesson Summaries | Auto-generated recap at end of each lesson | P2 — Should Have | Not available | Not built yet — no AI features in the app. | Later version
| Key takeaways in 3 bullet points |  | Not available | Not built yet — no AI features in the app. | Later version
| Glossary of terms introduced in lesson |  | Not available | Not built yet — no AI features in the app. | Later version
| Explain this differently button |  | Not available | Not built yet — no AI features in the app. | Later version
Personalised Study Planner | Goal date to reverse-engineered daily plan | P2 — Should Have | Not available | Not built yet — no AI features in the app. | Later version
| Adapts if learner falls behind |  | Not available | Not built yet — no AI features in the app. | Later version
| Morning briefing: Today's plan |  | Not available | Not built yet — no AI features in the app. | Later version
| Syncs with phone calendar (Google / Apple) |  | Not available | Not built yet — no AI features in the app. | Later version
AI-Powered Feedback | Auto-grade short answer and essay questions | P3 — Nice to Have | Not available | Not built yet — no AI features in the app. | Later version
| Writing style and clarity suggestions |  | Not available | Not built yet — no AI features in the app. | Later version
| Code review for tech courses |  | Not available | Not built yet — no AI features in the app. | Later version
| Pronunciation feedback for language courses |  | Not available | Not built yet — no AI features in the app. | Later version
Content Intelligence | Transcript search across all enrolled courses | P3 — Nice to Have | Not available | Not built yet — no AI features in the app. | Later version
| Find me a lesson about X (natural language search) |  | Not available | Not built yet — no AI features in the app. | Later version
| Related lessons recommendation engine |  | Not available | Not built yet — no AI features in the app. | Later version
| Knowledge gap detection across courses |  | Not available | Not built yet — no AI features in the app. | Later version

## Tier 6 - Platform and Ops
TIER 6 - PLATFORM AND OPS
Creator and admin tools
Feature Group | Feature / Description | Priority | App Status | In Our App Today / What's Missing | Recommendation
Instructor Dashboard (Mobile) | Revenue summary (today / week / month) | P1 — Must Have | Not available | The app is learner-only; no instructor dashboard. | Later version
| Enrolment count and trend |  | Not available | No enrolment stats in the app. | Later version
| Average course completion rate |  | Not available | No completion-rate reporting. | Later version
| Top-performing lessons |  | Not available | No lesson performance reporting. | Later version
| Student question queue |  | Not available | No question queue. | Later version
Analytics | Drop-off heatmap (where learners quit) | P1 — Must Have | Not available | No analytics. | Later version
| Video engagement (rewind / skip patterns) |  | Not available | No video engagement tracking. | Later version
| Quiz pass rate per question |  | Not available | No per-question quiz reports in the app (LearnDash has them on the website). | Later version
| Cohort comparison reports |  | Not available | No cohort reports. | Later version
| Revenue attribution per marketing channel |  | Not available | No revenue attribution. | Later version
Multi-Tenant / White Label | Custom brand colours and logo per school | P2 — Should Have | Partial | Colours, logo and site address are set per build in the app config; one app build per school, no runtime switching. | Later version
| Custom domain support |  | Partial | The app connects to any LearnDash site address set at build time. | Later version
| One codebase, config-file per tenant |  | Partial | One codebase; each school needs its own build with its own config. | Later version
| Separate instructor and student portals |  | Not available | Student app only. | Later version
| Per-tenant feature flag control |  | Not available | No per-tenant feature flags (only the plugin's licence/trial check). | Later version
Integrations | LearnDash / Kajabi / Teachable data sync | P2 — Should Have | Partial | Full LearnDash sync through the LearnDash Mobile API plugin (courses, progress, quizzes, certificates, offline completions). No Kajabi or Teachable. | Available now
| Zapier webhooks for automation |  | Not available | No Zapier webhooks. | Later version
| HubSpot / Mailchimp CRM sync |  | Not available | No CRM sync. | Later version
| Stripe / Razorpay / PayPal payment gateways |  | Not available | No payments in the app; gateways run on the website (WooCommerce/Stripe/PayPal). | Later version
| Google Analytics + Meta Pixel event tracking |  | Not available | No GA / Meta Pixel events. | Later version
Accessibility & Compliance | WCAG 2.1 AA compliance | P3 — Nice to Have | Not available | Not audited for WCAG 2.1 AA. | Later version
| Screen reader support (VoiceOver / TalkBack) |  | Partial | Some screen-reader labels (course cards, category chips, quiz); not tested with TalkBack / VoiceOver. | Next version
| Dyslexia-friendly font option |  | Not available | No dyslexia-friendly font option. | Later version
| GDPR / CCPA data controls |  | Not available | No privacy policy link or in-app account deletion. Google Play and the App Store require both for apps with login. | Next version
| SCORM / xAPI compatibility for corporate clients |  | Done | SCORM / xAPI modules (Tin Canny, CourseRelay) play inside the app and report completion. | Available now

## Pending Items
PENDING ITEMS — NOT AVAILABLE OR PARTIAL, BY TIER
Sorted by tier, then 'Next version' before 'Later version', then priority. Copied from the tier tabs on 15 Oct 2026 — update the tier tabs first if a status changes.
Tier | Feature Group | Feature | Priority | Status | What's Missing | Recommendation
Tier 1 — Core Learning | Video Player | Resume from last position | P1 — Must Have | Not available | Videos start from 0:00 every time; the playback position is not saved. | Next version
Tier 1 — Core Learning | Video Player | Subtitles / closed captions | P1 — Must Have | Partial | YouTube videos show YouTube's own captions where available. No subtitle support for self-hosted MP4 videos. | Next version
Tier 1 — Core Learning | Progress Tracking | Completion percentage on home screen | P1 — Must Have | Partial | Shown on the course page and Profile stats; the home-screen course cards do not show a percentage. | Next version
Tier 1 — Core Learning | Quizzes & Certificates | Drip-locked lessons (unlock on passing quiz) | P2 — Should Have | Partial | Drip by date and linear progression (next lesson locked until the previous one is done) work, also offline. Unlocking specifically on passing a quiz is not yet tested. | Next version
Tier 1 — Core Learning | Quizzes & Certificates | Shareable certificate (LinkedIn, PDF download) | P2 — Should Have | Partial | Certificate downloads as a PDF and opens in the phone's viewer (can be shared from there). No LinkedIn or in-app share button. | Next version
Tier 1 — Core Learning | Course Catalogue | Search by keyword, topic, instructor | P2 — Should Have | Partial | Search by keyword and by topic. No search by instructor. | Next version
Tier 1 — Core Learning | Course Catalogue | Filter by category, level, price, duration | P2 — Should Have | Partial | Filter by category only. No level, price or duration filters. | Next version
Tier 1 — Core Learning | Course Catalogue | Enrolment and one-click access | P2 — Should Have | Partial | Enrolled courses open in one tap (Start / Continue). Enrolling itself happens on the website. | Next version
Tier 1 — Core Learning | Video Player | Picture-in-picture mode | P1 — Must Have | Not available | No picture-in-picture; video stops when the app is minimised. | Later version
Tier 1 — Core Learning | Video Player | Quality selector (auto / 360p / 720p / 1080p) | P1 — Must Have | Partial | YouTube adjusts quality automatically; no manual selector. MP4 plays the uploaded file as-is. | Later version
Tier 1 — Core Learning | Quizzes & Certificates | Quiz retake limits and cooldown timers | P2 — Should Have | Partial | Retake limits are enforced by LearnDash when the quiz is submitted; the app does not show attempts left or a cooldown timer. | Later version
Tier 1 — Core Learning | Course Catalogue | Course preview (free trailer) | P2 — Should Have | Not available | No course trailer/preview in the app. | Later version
Tier 1 — Core Learning | Course Catalogue | Wishlist / save for later | P2 — Should Have | Not available | No wishlist / save for later. | Later version
Tier 2 — Engagement | Push Notifications | Daily learning reminders (user-set time) | P1 — Must Have | Not available | No push notifications. The app only notifies when a course download finishes. | Next version
Tier 2 — Engagement | Push Notifications | New lesson / content drop alerts | P1 — Must Have | Not available | No push alert. In-app only: a downloaded course shows 'Updated on the site — download again' when content changes. | Next version
Tier 2 — Engagement | Push Notifications | Streak alerts (Don't break your streak!) | P1 — Must Have | Not available | No streaks or streak alerts. | Later version
Tier 2 — Engagement | Push Notifications | Live session reminders | P1 — Must Have | Not available | No live sessions. | Later version
Tier 2 — Engagement | Push Notifications | Assignment due date reminders | P1 — Must Have | Not available | No assignments or due-date reminders. | Later version
Tier 2 — Engagement | Gamification | XP points per lesson completed | P1 — Must Have | Not available | No XP points. | Later version
Tier 2 — Engagement | Gamification | Badges and achievement unlocks | P1 — Must Have | Not available | No badges or achievements. | Later version
Tier 2 — Engagement | Gamification | Course leaderboard (opt-in) | P1 — Must Have | Not available | No leaderboard. | Later version
Tier 2 — Engagement | Gamification | Level system (Beginner to Expert) | P1 — Must Have | Not available | No level system. | Later version
Tier 2 — Engagement | Gamification | Monthly challenge events | P1 — Must Have | Not available | No challenge events. | Later version
Tier 2 — Engagement | Learning Streaks | Daily goal setting (15 min / 30 min / 1 hr) | P2 — Should Have | Not available | No daily goal setting. | Later version
Tier 2 — Engagement | Learning Streaks | Calendar heatmap of activity | P2 — Should Have | Not available | No activity heatmap. | Later version
Tier 2 — Engagement | Learning Streaks | Streak freeze (grace day) | P2 — Should Have | Not available | No streak freeze. | Later version
Tier 2 — Engagement | Learning Streaks | Weekly summary card | P2 — Should Have | Not available | No weekly summary. | Later version
Tier 2 — Engagement | Notes & Bookmarks | Timestamped notes inside video (tap to note at 4:32) | P2 — Should Have | Not available | No notes inside videos. | Later version
Tier 2 — Engagement | Notes & Bookmarks | Highlight key moments in transcripts | P2 — Should Have | Not available | No transcripts or highlights. | Later version
Tier 2 — Engagement | Notes & Bookmarks | Personal notebook per course | P2 — Should Have | Not available | No personal notebook. | Later version
Tier 2 — Engagement | Notes & Bookmarks | Export notes as PDF | P2 — Should Have | Not available | No notes export. | Later version
Tier 2 — Engagement | Assignments & Projects | File upload submissions | P3 — Nice to Have | Not available | No assignment uploads in the app (LearnDash assignments must be submitted on the website). | Later version
Tier 2 — Engagement | Assignments & Projects | Instructor feedback with annotations | P3 — Nice to Have | Not available | No instructor feedback view. | Later version
Tier 2 — Engagement | Assignments & Projects | Peer review workflows | P3 — Nice to Have | Not available | No peer review. | Later version
Tier 2 — Engagement | Assignments & Projects | Submission deadline tracking | P3 — Nice to Have | Not available | No deadline tracking. | Later version
Tier 3 — Community | Discussion Forums | Per-lesson comment threads | P1 — Must Have | Not available | No lesson comments. | Later version
Tier 3 — Community | Discussion Forums | Per-course community feed | P1 — Must Have | Not available | No community feed. | Later version
Tier 3 — Community | Discussion Forums | Upvote / mark as helpful | P1 — Must Have | Not available | No upvotes. | Later version
Tier 3 — Community | Discussion Forums | Instructor pinned answers | P1 — Must Have | Not available | No pinned answers. | Later version
Tier 3 — Community | Discussion Forums | Rich text + image attachments | P1 — Must Have | Not available | No rich-text posts. | Later version
Tier 3 — Community | Live Sessions | In-app Zoom / Google Meet integration | P1 — Must Have | Not available | No Zoom / Google Meet integration. | Later version
Tier 3 — Community | Live Sessions | Live session schedule on home screen | P1 — Must Have | Not available | No live session schedule. | Later version
Tier 3 — Community | Live Sessions | Replay recordings linked to course | P1 — Must Have | Not available | No recordings section. | Later version
Tier 3 — Community | Live Sessions | Q&A queue during live sessions | P1 — Must Have | Not available | No live Q&A. | Later version
Tier 3 — Community | Live Sessions | Attendance tracking | P1 — Must Have | Not available | No attendance tracking. | Later version
Tier 3 — Community | Cohort Groups | Batch-based groups (Jan cohort, March cohort) | P2 — Should Have | Not available | No cohort groups (LearnDash groups are not shown in the app). | Later version
Tier 3 — Community | Cohort Groups | Group chat per cohort | P2 — Should Have | Not available | No group chat. | Later version
Tier 3 — Community | Cohort Groups | Shared progress view within cohort | P2 — Should Have | Not available | No shared cohort progress. | Later version
Tier 3 — Community | Cohort Groups | Accountability partner matching | P2 — Should Have | Not available | No partner matching. | Later version
Tier 3 — Community | Instructor Direct Message | Async Q&A with instructor | P2 — Should Have | Not available | No instructor messaging. | Later version
Tier 3 — Community | Instructor Direct Message | Voice message support | P2 — Should Have | Not available | No voice messages. | Later version
Tier 3 — Community | Instructor Direct Message | Response time indicator | P2 — Should Have | Not available | No response-time indicator. | Later version
Tier 3 — Community | Instructor Direct Message | Office hours booking (Calendly integration) | P2 — Should Have | Not available | No office-hours booking. | Later version
Tier 3 — Community | Peer Networking | Learner profiles (skills, goals, location) | P3 — Nice to Have | Not available | Profile shows the learner's own name and course stats only. | Later version
Tier 3 — Community | Peer Networking | Connect / follow other learners | P3 — Nice to Have | Not available | No follow/connect. | Later version
Tier 3 — Community | Peer Networking | Course alumni directory | P3 — Nice to Have | Not available | No alumni directory. | Later version
Tier 3 — Community | Peer Networking | Study group creation | P3 — Nice to Have | Not available | No study groups. | Later version
Tier 4 — Monetisation | Free vs Paid Gating | Free preview lessons per course | P3 — Nice to Have | Not available | LearnDash sample (free preview) lessons are not shown as previews to non-enrolled learners. | Next version
Tier 4 — Monetisation | Free vs Paid Gating | Upgrade prompt at paywall moment | P3 — Nice to Have | Partial | Non-enrolled learners see 'Access Restricted'; there is no upgrade or buy link to the website. | Next version
Tier 4 — Monetisation | In-App Purchases | Individual course purchases | P1 — Must Have | Not available | No in-app purchase; courses are bought on the website (see the note in row 9). | Later version
Tier 4 — Monetisation | In-App Purchases | Bundle / programme purchases | P1 — Must Have | Not available | No bundle purchases in the app. | Later version
Tier 4 — Monetisation | In-App Purchases | Upsell prompts at course completion | P1 — Must Have | Not available | No upsell prompts. | Later version
Tier 4 — Monetisation | In-App Purchases | One-click buy with saved payment method | P1 — Must Have | Not available | No in-app payments. | Later version
Tier 4 — Monetisation | Subscriptions | Monthly and annual plan options | P1 — Must Have | Not available | No subscriptions in the app (handled on the website). | Later version
Tier 4 — Monetisation | Subscriptions | All-access vs category-specific tiers | P1 — Must Have | Not available | No subscription tiers in the app. | Later version
Tier 4 — Monetisation | Subscriptions | Free trial with card capture | P1 — Must Have | Not available | No trial capture in the app. (The plugin's 15-day trial is a site licence, not a learner trial.) | Later version
Tier 4 — Monetisation | Subscriptions | Pause subscription option | P1 — Must Have | Not available | No pause option. | Later version
Tier 4 — Monetisation | Subscriptions | Family / team plan | P1 — Must Have | Not available | No family/team plans. | Later version
Tier 4 — Monetisation | Promo Codes & Affiliates | Discount code entry at checkout | P2 — Should Have | Not available | No checkout in the app. | Later version
Tier 4 — Monetisation | Promo Codes & Affiliates | Affiliate link tracking | P2 — Should Have | Not available | No affiliate tracking. | Later version
Tier 4 — Monetisation | Promo Codes & Affiliates | Referral rewards for learners | P2 — Should Have | Not available | No referral rewards. | Later version
Tier 4 — Monetisation | Promo Codes & Affiliates | Flash sale banners | P2 — Should Have | Not available | No sale banners. | Later version
Tier 4 — Monetisation | Wallet & Credits | In-app credit balance | P2 — Should Have | Not available | No credit balance. | Later version
Tier 4 — Monetisation | Wallet & Credits | Gift cards (send to a friend) | P2 — Should Have | Not available | No gift cards. | Later version
Tier 4 — Monetisation | Wallet & Credits | Bulk seat purchasing for teams | P2 — Should Have | Not available | No bulk seats in the app. | Later version
Tier 4 — Monetisation | Wallet & Credits | Corporate invoice / PO support | P2 — Should Have | Not available | No invoice / PO support in the app. | Later version
Tier 4 — Monetisation | Free vs Paid Gating | Lead magnet free course to paid upsell | P3 — Nice to Have | Not available | Free courses are marked FREE, but there is no free-to-paid upsell flow. | Later version
Tier 5 — AI Layer | AI Tutor / Course Q&A | Course-scoped chatbot (only knows your content) | P1 — Must Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | AI Tutor / Course Q&A | Ask questions about a lesson mid-video | P1 — Must Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | AI Tutor / Course Q&A | Socratic mode (guides, doesn't just answer) | P1 — Must Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | AI Tutor / Course Q&A | Cites the exact lesson or timestamp for the answer | P1 — Must Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | AI Tutor / Course Q&A | BYOK model support for enterprise clients | P1 — Must Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | Adaptive Learning Paths | Pre-assessment to place learner in right module | P1 — Must Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | Adaptive Learning Paths | Skip lessons the learner already knows | P1 — Must Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | Adaptive Learning Paths | Resurface lessons where quiz scores were low | P1 — Must Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | Adaptive Learning Paths | Dynamic reordering based on learning pace | P1 — Must Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | Smart Lesson Summaries | Auto-generated recap at end of each lesson | P2 — Should Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | Smart Lesson Summaries | Key takeaways in 3 bullet points | P2 — Should Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | Smart Lesson Summaries | Glossary of terms introduced in lesson | P2 — Should Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | Smart Lesson Summaries | Explain this differently button | P2 — Should Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | Personalised Study Planner | Goal date to reverse-engineered daily plan | P2 — Should Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | Personalised Study Planner | Adapts if learner falls behind | P2 — Should Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | Personalised Study Planner | Morning briefing: Today's plan | P2 — Should Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | Personalised Study Planner | Syncs with phone calendar (Google / Apple) | P2 — Should Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | AI-Powered Feedback | Auto-grade short answer and essay questions | P3 — Nice to Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | AI-Powered Feedback | Writing style and clarity suggestions | P3 — Nice to Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | AI-Powered Feedback | Code review for tech courses | P3 — Nice to Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | AI-Powered Feedback | Pronunciation feedback for language courses | P3 — Nice to Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | Content Intelligence | Transcript search across all enrolled courses | P3 — Nice to Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | Content Intelligence | Find me a lesson about X (natural language search) | P3 — Nice to Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | Content Intelligence | Related lessons recommendation engine | P3 — Nice to Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 5 — AI Layer | Content Intelligence | Knowledge gap detection across courses | P3 — Nice to Have | Not available | Not built yet — no AI features in the app. | Later version
Tier 6 — Platform and Ops | Accessibility & Compliance | Screen reader support (VoiceOver / TalkBack) | P3 — Nice to Have | Partial | Some screen-reader labels (course cards, category chips, quiz); not tested with TalkBack / VoiceOver. | Next version
Tier 6 — Platform and Ops | Accessibility & Compliance | GDPR / CCPA data controls | P3 — Nice to Have | Not available | No privacy policy link or in-app account deletion. Google Play and the App Store require both for apps with login. | Next version
Tier 6 — Platform and Ops | Instructor Dashboard (Mobile) | Revenue summary (today / week / month) | P1 — Must Have | Not available | The app is learner-only; no instructor dashboard. | Later version
Tier 6 — Platform and Ops | Instructor Dashboard (Mobile) | Enrolment count and trend | P1 — Must Have | Not available | No enrolment stats in the app. | Later version
Tier 6 — Platform and Ops | Instructor Dashboard (Mobile) | Average course completion rate | P1 — Must Have | Not available | No completion-rate reporting. | Later version
Tier 6 — Platform and Ops | Instructor Dashboard (Mobile) | Top-performing lessons | P1 — Must Have | Not available | No lesson performance reporting. | Later version
Tier 6 — Platform and Ops | Instructor Dashboard (Mobile) | Student question queue | P1 — Must Have | Not available | No question queue. | Later version
Tier 6 — Platform and Ops | Analytics | Drop-off heatmap (where learners quit) | P1 — Must Have | Not available | No analytics. | Later version
Tier 6 — Platform and Ops | Analytics | Video engagement (rewind / skip patterns) | P1 — Must Have | Not available | No video engagement tracking. | Later version
Tier 6 — Platform and Ops | Analytics | Quiz pass rate per question | P1 — Must Have | Not available | No per-question quiz reports in the app (LearnDash has them on the website). | Later version
Tier 6 — Platform and Ops | Analytics | Cohort comparison reports | P1 — Must Have | Not available | No cohort reports. | Later version
Tier 6 — Platform and Ops | Analytics | Revenue attribution per marketing channel | P1 — Must Have | Not available | No revenue attribution. | Later version
Tier 6 — Platform and Ops | Multi-Tenant / White Label | Custom brand colours and logo per school | P2 — Should Have | Partial | Colours, logo and site address are set per build in the app config; one app build per school, no runtime switching. | Later version
Tier 6 — Platform and Ops | Multi-Tenant / White Label | Custom domain support | P2 — Should Have | Partial | The app connects to any LearnDash site address set at build time. | Later version
Tier 6 — Platform and Ops | Multi-Tenant / White Label | One codebase, config-file per tenant | P2 — Should Have | Partial | One codebase; each school needs its own build with its own config. | Later version
Tier 6 — Platform and Ops | Multi-Tenant / White Label | Separate instructor and student portals | P2 — Should Have | Not available | Student app only. | Later version
Tier 6 — Platform and Ops | Multi-Tenant / White Label | Per-tenant feature flag control | P2 — Should Have | Not available | No per-tenant feature flags (only the plugin's licence/trial check). | Later version
Tier 6 — Platform and Ops | Integrations | Zapier webhooks for automation | P2 — Should Have | Not available | No Zapier webhooks. | Later version
Tier 6 — Platform and Ops | Integrations | HubSpot / Mailchimp CRM sync | P2 — Should Have | Not available | No CRM sync. | Later version
Tier 6 — Platform and Ops | Integrations | Stripe / Razorpay / PayPal payment gateways | P2 — Should Have | Not available | No payments in the app; gateways run on the website (WooCommerce/Stripe/PayPal). | Later version
Tier 6 — Platform and Ops | Integrations | Google Analytics + Meta Pixel event tracking | P2 — Should Have | Not available | No GA / Meta Pixel events. | Later version
Tier 6 — Platform and Ops | Accessibility & Compliance | WCAG 2.1 AA compliance | P3 — Nice to Have | Not available | Not audited for WCAG 2.1 AA. | Later version
Tier 6 — Platform and Ops | Accessibility & Compliance | Dyslexia-friendly font option | P3 — Nice to Have | Not available | No dyslexia-friendly font option. | Later version
Tier 6 — Platform and Ops | Integrations | LearnDash / Kajabi / Teachable data sync | P2 — Should Have | Partial | Full LearnDash sync through the LearnDash Mobile API plugin (courses, progress, quizzes, certificates, offline completions). No Kajabi or Teachable. | Available now

## Available Now
AVAILABLE IN THE APP TODAY
Tier / Area | Feature Group | Feature | Status | How It Works in the App
Tier 1 — Core Learning | Video Player | Offline download for on-the-go learning | Done | Whole course downloads for offline use: MP4 videos, lesson text, images and materials, with pause/resume/cancel, progress and notifications. YouTube/Vimeo lessons still need internet.
Tier 1 — Core Learning | Video Player | Playback speed controls (0.5x to 2x) | Done | 0.5x to 2x speed for self-hosted MP4 (player menu) and YouTube (speed chip).
Tier 1 — Core Learning | Progress Tracking | Per-lesson completion status | Done | Tick per lesson/topic in the curriculum, including progress made offline.
Tier 1 — Core Learning | Progress Tracking | Per-course progress bar | Done | Progress bar and 'X of Y completed' on the course page.
Tier 1 — Core Learning | Progress Tracking | Resume where you left off | Done | 'Continue' opens the next unfinished lesson; works offline for downloaded courses.
Tier 1 — Core Learning | Quizzes & Certificates | Multiple choice, true/false, short answer | Done | Native in-app quiz: single and multiple choice (incl. true/false), free-text answer, sorting, fill-in-the-blank, matrix and assessment questions.
Tier 1 — Core Learning | Quizzes & Certificates | Auto-generated completion certificates | Done | LearnDash certificate is available in the app once the course is completed.
Tier 1 — Core Learning | Video Player | Subtitles / closed captions | Partial | YouTube videos show YouTube's own captions where available. No subtitle support for self-hosted MP4 videos.
Tier 1 — Core Learning | Video Player | Quality selector (auto / 360p / 720p / 1080p) | Partial | YouTube adjusts quality automatically; no manual selector. MP4 plays the uploaded file as-is.
Tier 1 — Core Learning | Progress Tracking | Completion percentage on home screen | Partial | Shown on the course page and Profile stats; the home-screen course cards do not show a percentage.
Tier 1 — Core Learning | Quizzes & Certificates | Drip-locked lessons (unlock on passing quiz) | Partial | Drip by date and linear progression (next lesson locked until the previous one is done) work, also offline. Unlocking specifically on passing a quiz is not yet tested.
Tier 1 — Core Learning | Quizzes & Certificates | Shareable certificate (LinkedIn, PDF download) | Partial | Certificate downloads as a PDF and opens in the phone's viewer (can be shared from there). No LinkedIn or in-app share button.
Tier 1 — Core Learning | Quizzes & Certificates | Quiz retake limits and cooldown timers | Partial | Retake limits are enforced by LearnDash when the quiz is submitted; the app does not show attempts left or a cooldown timer.
Tier 1 — Core Learning | Course Catalogue | Search by keyword, topic, instructor | Partial | Search by keyword and by topic. No search by instructor.
Tier 1 — Core Learning | Course Catalogue | Filter by category, level, price, duration | Partial | Filter by category only. No level, price or duration filters.
Tier 1 — Core Learning | Course Catalogue | Enrolment and one-click access | Partial | Enrolled courses open in one tap (Start / Continue). Enrolling itself happens on the website.
Tier 4 — Monetisation | Free vs Paid Gating | Locked lesson indicators | Done | Lock icons with reasons: 'Complete the previous lesson', drip date ('Available on …'), access expired or removed.
Tier 4 — Monetisation | Free vs Paid Gating | Upgrade prompt at paywall moment | Partial | Non-enrolled learners see 'Access Restricted'; there is no upgrade or buy link to the website.
Tier 6 — Platform and Ops | Accessibility & Compliance | SCORM / xAPI compatibility for corporate clients | Done | SCORM / xAPI modules (Tin Canny, CourseRelay) play inside the app and report completion.
Tier 6 — Platform and Ops | Multi-Tenant / White Label | Custom brand colours and logo per school | Partial | Colours, logo and site address are set per build in the app config; one app build per school, no runtime switching.
Tier 6 — Platform and Ops | Multi-Tenant / White Label | Custom domain support | Partial | The app connects to any LearnDash site address set at build time.
Tier 6 — Platform and Ops | Multi-Tenant / White Label | One codebase, config-file per tenant | Partial | One codebase; each school needs its own build with its own config.
Tier 6 — Platform and Ops | Integrations | LearnDash / Kajabi / Teachable data sync | Partial | Full LearnDash sync through the LearnDash Mobile API plugin (courses, progress, quizzes, certificates, offline completions). No Kajabi or Teachable.
Tier 6 — Platform and Ops | Accessibility & Compliance | Screen reader support (VoiceOver / TalkBack) | Partial | Some screen-reader labels (course cards, category chips, quiz); not tested with TalkBack / VoiceOver.
ALSO IN THE APP — NOT LISTED IN THE FEATURE SHEET
Offline | Extra | Lessons completed offline sync automatically when back online, with their original completion time | Done | Not in the feature sheet
Offline | Extra | Drip dates, linear progression, access expiry and removed access are enforced offline (tamper-resistant clock) | Done | Not in the feature sheet
Offline | Extra | Detects when a downloaded course was updated on the site and offers to download it again | Done | Not in the feature sheet
Offline | Extra | 'Sync issues' list for progress the site refused (e.g. access ended), with a plain-language reason | Done | Not in the feature sheet
Content | Extra | Course materials and downloadable files open in an in-app viewer | Done | Not in the feature sheet
Content | Extra | Elementor-built lessons and Vimeo embeds render in the app | Done | Not in the feature sheet
Content | Extra | Lesson images saved for offline reading | Done | Not in the feature sheet
Account | Extra | Sign in with the learner's existing website account | Done | Not in the feature sheet
Account | Extra | Profile with enrolled / completed course stats | Done | Not in the feature sheet
Platform | Extra | Clear 'Connection problem' screen with a shortcut to downloaded courses | Done | Not in the feature sheet
Platform | Extra | Android 16 KB page-size support (required for new Play Store builds) | Done | Not in the feature sheet

## Partial Features
PARTIALLY DONE FEATURES — WHAT WORKS AND WHAT IS LEFT
Features that work in part today. Effort is a rough estimate for one developer: S = up to 3 days, M = 1-2 weeks, L = 3+ weeks.
# | Tier | Feature Group | Feature | Works Today | Left to Finish | Effort | Plugin Change?
1 | Tier 1 — Core Learning | Video Player | Subtitles / closed captions | YouTube videos show YouTube's own captions where available. No subtitle support for self-hosted MP4 videos. | Add subtitle tracks (.vtt) for self-hosted MP4 videos: plugin sends caption files from the lesson, player shows a CC toggle. | M | Yes
2 | Tier 1 — Core Learning | Video Player | Quality selector (auto / 360p / 720p / 1080p) | YouTube adjusts quality automatically; no manual selector. MP4 plays the uploaded file as-is. | Manual quality picker needs multiple renditions of each video (or HLS streaming); not possible with a single uploaded MP4. | L | Yes
3 | Tier 1 — Core Learning | Progress Tracking | Completion percentage on home screen | Shown on the course page and Profile stats; the home-screen course cards do not show a percentage. | Show the progress % and bar on home-screen course cards (data already comes from the site). | S | No
4 | Tier 1 — Core Learning | Quizzes & Certificates | Drip-locked lessons (unlock on passing quiz) | Drip by date and linear progression (next lesson locked until the previous one is done) work, also offline. Unlocking specifically on passing a quiz is not yet tested. | Test a course with a quiz as a prerequisite; if needed, re-check the next lesson's lock right after the quiz is passed. | S | Maybe
5 | Tier 1 — Core Learning | Quizzes & Certificates | Shareable certificate (LinkedIn, PDF download) | Certificate downloads as a PDF and opens in the phone's viewer (can be shared from there). No LinkedIn or in-app share button. | Add a Share button (system share sheet) for the certificate PDF and an 'Add to LinkedIn' link. | S | No
6 | Tier 1 — Core Learning | Quizzes & Certificates | Quiz retake limits and cooldown timers | Retake limits are enforced by LearnDash when the quiz is submitted; the app does not show attempts left or a cooldown timer. | Show attempts left / next retake time on the quiz screen, using LearnDash's quiz repeat settings. | S | Yes
7 | Tier 1 — Core Learning | Course Catalogue | Search by keyword, topic, instructor | Search by keyword and by topic. No search by instructor. | Add instructor as a search option (author name) next to keyword and topic. | S | Yes
8 | Tier 1 — Core Learning | Course Catalogue | Filter by category, level, price, duration | Filter by category only. No level, price or duration filters. | Add filters for price (free/paid) and duration; 'level' needs a course field or tag on the site. | M | Yes
9 | Tier 1 — Core Learning | Course Catalogue | Enrolment and one-click access | Enrolled courses open in one tap (Start / Continue). Enrolling itself happens on the website. | Add an 'Enrol' button for free/open courses and a 'Buy on website' link for paid ones. | M | Yes
10 | Tier 4 — Monetisation | Free vs Paid Gating | Upgrade prompt at paywall moment | Non-enrolled learners see 'Access Restricted'; there is no upgrade or buy link to the website. | On a locked course, add an 'Enrol / Buy on website' button that opens the course page in the browser. | S | No
11 | Tier 6 — Platform and Ops | Multi-Tenant / White Label | Custom brand colours and logo per school | Colours, logo and site address are set per build in the app config; one app build per school, no runtime switching. | Move colours, logo and app name into one per-school config file used at build time. | M | No
12 | Tier 6 — Platform and Ops | Multi-Tenant / White Label | Custom domain support | The app connects to any LearnDash site address set at build time. | Same as above: the site address is already in config; document the per-school build steps. | S | No
13 | Tier 6 — Platform and Ops | Multi-Tenant / White Label | One codebase, config-file per tenant | One codebase; each school needs its own build with its own config. | Add a build script that produces one app per school from its config. | M | No
14 | Tier 6 — Platform and Ops | Integrations | LearnDash / Kajabi / Teachable data sync | Full LearnDash sync through the LearnDash Mobile API plugin (courses, progress, quizzes, certificates, offline completions). No Kajabi or Teachable. | LearnDash is fully covered; Kajabi/Teachable would each need a separate integration. | L | Yes
15 | Tier 6 — Platform and Ops | Accessibility & Compliance | Screen reader support (VoiceOver / TalkBack) | Some screen-reader labels (course cards, category chips, quiz); not tested with TalkBack / VoiceOver. | Add screen-reader labels to all buttons and icons; test with TalkBack and VoiceOver. | M | No

## Next Features
NEXT FEATURES — SUGGESTED FOR THE NEXT VERSION
Features marked 'Next version' on the tier tabs, in a suggested build order (store requirements and quick wins first). Effort is a rough estimate for one developer: S = up to 3 days, M = 1-2 weeks, L = 3+ weeks.
Order | Tier | Feature Group | Feature | Priority | Status Today | Why Next | Effort | Plugin Change?
1 | Tier 6 — Platform and Ops | Accessibility & Compliance | GDPR / CCPA data controls | P3 — Nice to Have | Not available | Required by Google Play and the App Store for any app with a login: privacy policy link and in-app account deletion. Blocks store release. | S | Yes
2 | Tier 1 — Core Learning | Video Player | Resume from last position | P1 — Must Have | Not available | Learners lose their place in long videos every time they leave a lesson. | S | No
3 | Tier 1 — Core Learning | Progress Tracking | Completion percentage on home screen | P1 — Must Have | Partial | Data is already in the app; quick win on the main screen. | S | No
4 | Tier 4 — Monetisation | Free vs Paid Gating | Upgrade prompt at paywall moment | P3 — Nice to Have | Partial | Non-enrolled learners hit a dead end today; a link to the course page on the website fixes it. | S | No
5 | Tier 1 — Core Learning | Quizzes & Certificates | Shareable certificate (LinkedIn, PDF download) | P2 — Should Have | Partial | Small addition to the existing certificate download; learners expect to share it. | S | No
6 | Tier 1 — Core Learning | Quizzes & Certificates | Drip-locked lessons (unlock on passing quiz) | P2 — Should Have | Partial | Mostly a test of existing behaviour with a quiz-gated course; fix only if it does not unlock. | S | Maybe
7 | Tier 1 — Core Learning | Course Catalogue | Enrolment and one-click access | P2 — Should Have | Partial | Lets learners enrol in free courses from the app instead of going to the website. | M | Yes
8 | Tier 4 — Monetisation | Free vs Paid Gating | Free preview lessons per course | P3 — Nice to Have | Not available | LearnDash 'sample lessons' already exist on the site; showing them lets learners try before enrolling. | M | Yes
9 | Tier 1 — Core Learning | Course Catalogue | Search by keyword, topic, instructor | P2 — Should Have | Partial | Search by instructor completes the catalogue search. | S | Yes
10 | Tier 1 — Core Learning | Course Catalogue | Filter by category, level, price, duration | P2 — Should Have | Partial | Price and duration filters for larger catalogues. | M | Yes
11 | Tier 2 — Engagement | Push Notifications | Daily learning reminders (user-set time) | P1 — Must Have | Not available | First step into push notifications (Firebase); daily reminders lift completion rates. | M | Yes
12 | Tier 2 — Engagement | Push Notifications | New lesson / content drop alerts | P1 — Must Have | Not available | Uses the same push setup; the site already knows when content changes. | M | Yes
13 | Tier 1 — Core Learning | Video Player | Subtitles / closed captions | P1 — Must Have | Partial | Captions for self-hosted videos (accessibility and non-native speakers). | M | Yes
14 | Tier 6 — Platform and Ops | Accessibility & Compliance | Screen reader support (VoiceOver / TalkBack) | P3 — Nice to Have | Partial | Screen-reader labels and a TalkBack/VoiceOver pass; also helps store review. | M | No